## Read me first
PORTABOX SEO BUILD SHEET
What this is | 126 items to build, in the order to build them. Work top to bottom. Set column C as you go.
Batch 1 | Quick wins. No page building. Four Google profiles, four title rewrites, three technical files. Do these first, they take a day and nothing else depends on them.
Batch 2 | Eight region hubs. Every suburb page links up to one of these, so they must exist before the suburb pages.
Batches 3 to 5 | The rescue. 43 suburb pages that already rank on auspods.com.au and convert almost nobody. Highest value work in the project.
Batch 6 | Six format pages. /storage-pods/ is the single highest value new page.
Batch 7 | Twenty interstate route pages. Lowest difficulty and highest CPC in the whole plan.
Batch 8 | Box shop. 18 thin pages consolidate into four aimed at "moving boxes", 18,100 searches a month.
Batch 9 | Comparison and trust. /formerly-pods-australia/ is launch critical.
Batch 10 | 28 pages to review, not build. Decide merge or rebuild for each. Do not migrate them as they are.
COLUMN KEY
Searches/mo | Australian monthly search volume from Ubersuggest. Blank means not individually measured.
GSC impressions | Impressions this page or query already earns on auspods.com.au in the last reporting period.
Current pos | Average Google position today. Under 12 means it already ranks on page one.
Old URL to 301 | The auspods.com.au URL that must redirect here. One hop, no chains.
Nearest depot | Used for the depot distance and drive time fields on the page.
BEFORE YOU START
Rows marked CHECK FIRST | Seven suburb names exist in more than one Australian state. Confirm the state before building, or the page lands in the wrong region hub.
Every suburb page needs | Depot distance in km, drive time, delivery lead time, whether the council requires a kerbside permit, and the nearby suburb list. A page cannot publish with those blank.
Do not build | A page targeting "storage containers". That query returns Bunnings, IKEA and Kmart. The intent is plastic food containers.
THE FOUR DEPOTS
Brisbane | 9 Citywest Court, Gilberton QLD 4208 · 07 3053 8770
Sydney | 20 Carnegie Place, Blacktown NSW 2148 · 02 8310 8188
Melbourne | 103 Fitzgerald Road, Laverton North VIC 3026 · 03 8375 8770
Adelaide | 10 Barfield Crescent, Edinburgh North SA 5113 · 08 7160 3333
Source | Google Search Console for auspods.com.au, 1,000 queries and 249 pages, exported 12 October 2026. Search volumes from Ubersuggest, Australia. Prepared by Propel Podiatry Profits.

## Build sheet
Batch | # | Status | Page type | New URL | Target keyword | Searches/mo | GSC impressions | Current pos | Action | Old URL to 301 | Nearest depot | What to do | Full link | Status | Notes
1. Quick wins, no build | 1 |  | Google Business Profile | GBP: Brisbane depot | storage near me | 12100 | 5303 |  | Optimise |  | 9 Citywest Court, Gilberton QLD 4208 | Claimed and verified already. Set service area to the delivery radius, correct primary category, add photos, enable Q&A, request a review after every delivery |  | Not a page | Not a page on this site. These are Google listings and the SEO team said to leave them for now.
1. Quick wins, no build | 2 |  | Google Business Profile | GBP: Sydney depot | storage near me | 12100 |  |  | Optimise |  | 20 Carnegie Place, Blacktown NSW 2148 | Claimed and verified already. Set service area to the delivery radius, correct primary category, add photos, enable Q&A, request a review after every delivery |  | Not a page | Not a page on this site. These are Google listings and the SEO team said to leave them for now.
1. Quick wins, no build | 3 |  | Google Business Profile | GBP: Melbourne depot | storage near me | 12100 |  |  | Optimise |  | 103 Fitzgerald Rd, Laverton North VIC 3026 | Claimed and verified already. Set service area to the delivery radius, correct primary category, add photos, enable Q&A, request a review after every delivery |  | Not a page | Not a page on this site. These are Google listings and the SEO team said to leave them for now.
1. Quick wins, no build | 4 |  | Google Business Profile | GBP: Adelaide depot | storage near me | 12100 |  |  | Optimise |  | 10 Barfield Cres, Edinburgh North SA 5113 | Claimed and verified already. Set service area to the delivery radius, correct primary category, add photos, enable Q&A, request a review after every delivery |  | Not a page | Not a page on this site. These are Google listings and the SEO team said to leave them for now.
1. Quick wins, no build | 5 |  | Title fix | /self-storage/brisbane/ | self storage brisbane | 2400 |  |  | Rewrite title | Storage & Moving Containers in South East Queensland |  | Title and H1 become "Self Storage Brisbane". Current title targets a phrase nobody searches | https://portabox-website.vercel.app/self-storage/brisbane/ | Live
1. Quick wins, no build | 6 |  | Title fix | /self-storage/sydney/ | self storage sydney | 2900 |  |  | Rewrite title | Storage & Moving Containers in Greater Sydney |  | Title and H1 become "Self Storage Sydney". Current title targets a phrase nobody searches | https://portabox-website.vercel.app/self-storage/sydney/ | Live
1. Quick wins, no build | 7 |  | Title fix | /self-storage/melbourne/ | self storage melbourne | 3600 |  |  | Rewrite title | Storage & Moving Containers in Victoria |  | Title and H1 become "Self Storage Melbourne". Current title targets a phrase nobody searches | https://portabox-website.vercel.app/self-storage/melbourne/ | Live
1. Quick wins, no build | 8 |  | Title fix | /self-storage/adelaide/ | self storage adelaide | 2400 |  |  | Rewrite title | Storage & Moving Containers in South Australia |  | Title and H1 become "Self Storage Adelaide". Current title targets a phrase nobody searches | https://portabox-website.vercel.app/self-storage/adelaide/ | Live
1. Quick wins, no build | 9 |  | Technical | robots.txt |  |  |  |  | Build |  |  | Create. Allow all, point to the sitemap | https://portabox-website.vercel.app/robots.txt | Live
1. Quick wins, no build | 10 |  | Technical | sitemap.xml |  |  |  |  | Build |  |  | Create. Every live URL, auto generated, submitted in Search Console | https://portabox-website.vercel.app/sitemap.xml | Live
1. Quick wins, no build | 11 |  | Technical | JSON-LD schema layer |  |  |  |  | Build |  |  | Build. Zero structured data exists on the site today |  | Not a page | BUILT, but not as a page: the schema is generated into the head of all 127 pages — Organization everywhere, SelfStorage on each region hub and facility, FAQPage and BreadcrumbList where they apply.
2. Region hubs | 12 |  | Region hub | /self-storage/brisbane/ | storage brisbane | 2400 |  |  | Build | /locations/brisbane/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/brisbane/ | Live
2. Region hubs | 13 |  | Region hub | /self-storage/sydney/ | self storage sydney | 2900 |  |  | Build | /locations/sydney/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/sydney/ | Live
2. Region hubs | 14 |  | Region hub | /self-storage/melbourne/ | self storage melbourne | 3600 |  |  | Build | /locations/melbourne/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/melbourne/ | Live
2. Region hubs | 15 |  | Region hub | /self-storage/adelaide/ | self storage adelaide | 2400 |  |  | Build | /locations/adelaide/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/adelaide/ | Live
2. Region hubs | 16 |  | Region hub | /self-storage/gold-coast/ | self storage gold coast |  |  |  | Build | /locations/gold-coast/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/gold-coast/ | Live
2. Region hubs | 17 |  | Region hub | /self-storage/central-coast/ | self storage central coast |  |  |  | Build | /locations/central-coast/ (301 to here) |  | Lists every suburb beneath it. Targets the city head term | https://portabox-website.vercel.app/self-storage/central-coast/ | Live
2. Region hubs | 18 |  | Region hub | /self-storage/newcastle/ | self storage newcastle |  | 2 |  | Build |  | Blacktown NSW | New market. Inside the Blacktown radius. Newcastle shows 130 query variants and earns 2 impressions today | https://portabox-website.vercel.app/self-storage/newcastle/ | Live
2. Region hubs | 19 |  | Region hub | /self-storage/wollongong/ | self storage wollongong |  | 0 |  | Build |  | Blacktown NSW | New market. Inside the Blacktown radius. Newcastle shows 130 query variants and earns 2 impressions today | https://portabox-website.vercel.app/self-storage/wollongong/ | Live
3. Rescue: top 10 | 20 |  | Suburb page | /self-storage/central-coast/west-gosford/ | storage west gosford |  | 16460 | 11.5 | Rebuild | /locations/west-gosford/ | Blacktown NSW | Currently position 11.5 with 24 clicks from 16460 impressions | https://portabox-website.vercel.app/self-storage/central-coast/west-gosford/ | Live
3. Rescue: top 10 | 21 |  | Suburb page | /self-storage/melbourne/hoppers-crossing/ | storage hoppers crossing |  | 12151 | 11.9 | Rebuild | /locations/hoppers-crossing/ | Laverton North VIC | Currently position 11.9 with 5 clicks from 12151 impressions | https://portabox-website.vercel.app/self-storage/melbourne/hoppers-crossing/ | Live
3. Rescue: top 10 | 22 |  | Suburb page | /self-storage/melbourne/box-hill/ | storage box hill |  | 11933 | 10.3 | Rebuild | /locations/box-hill/ | Laverton North VIC | Currently position 10.3 with 4 clicks from 11933 impressions | https://portabox-website.vercel.app/self-storage/melbourne/box-hill/ | Live
3. Rescue: top 10 | 23 |  | Suburb page | /self-storage/adelaide/port-adelaide/ | storage port adelaide |  | 8914 | 24.6 | Rebuild | /locations/port-adelaide/ | Edinburgh North SA | Currently position 24.6 with 14 clicks from 8914 impressions | https://portabox-website.vercel.app/self-storage/adelaide/port-adelaide/ | Live
3. Rescue: top 10 | 24 |  | Suburb page | /self-storage/brisbane/ipswich/ | storage ipswich |  | 8336 | 17.9 | Rebuild | /locations/ipswich/ | Gilberton QLD | Currently position 17.9 with 16 clicks from 8336 impressions | https://portabox-website.vercel.app/self-storage/brisbane/ipswich/ | Live
3. Rescue: top 10 | 25 |  | Suburb page | /self-storage/sydney/blacktown/ | storage blacktown |  | 8149 | 12.3 | Rebuild | /locations/blacktown/ | Blacktown NSW | Currently position 12.3 with 13 clicks from 8149 impressions | https://portabox-website.vercel.app/self-storage/sydney/blacktown/ | Live
3. Rescue: top 10 | 26 |  | Suburb page | /self-storage/gold-coast/tweed-heads/ | storage tweed heads |  | 7062 | 8.7 | Rebuild | /locations/tweed-heads/ | Gilberton QLD | Currently position 8.7 with 17 clicks from 7062 impressions | https://portabox-website.vercel.app/self-storage/gold-coast/tweed-heads/ | Live
3. Rescue: top 10 | 27 |  | Suburb page | /self-storage/sydney/castle-hill/ | storage castle hill |  | 6527 | 16.4 | Rebuild | /locations/castle-hill/ | Blacktown NSW | Currently position 16.4 with 3 clicks from 6527 impressions | https://portabox-website.vercel.app/self-storage/sydney/castle-hill/ | Live
3. Rescue: top 10 | 28 |  | Suburb page | /self-storage/brisbane/browns-plains/ | storage browns plains |  | 6465 | 19 | Rebuild | /locations/browns-plains/ | Gilberton QLD | Currently position 19.0 with 2 clicks from 6465 impressions | https://portabox-website.vercel.app/self-storage/brisbane/browns-plains/ | Live
3. Rescue: top 10 | 29 |  | Suburb page | /self-storage/melbourne/pakenham/ | storage pakenham |  | 5039 | 15.6 | Rebuild | /locations/pakenham/ | Laverton North VIC | Currently position 15.6 with 2 clicks from 5039 impressions | https://portabox-website.vercel.app/self-storage/melbourne/pakenham/ | Live
4. Rescue: next 16 | 30 |  | Suburb page | /self-storage/central-coast/rutherford/ | storage rutherford |  | 4968 | 7.9 | Rebuild | /locations/rutherford/ | Blacktown NSW | Currently position 7.9 with 2 clicks from 4968 impressions | https://portabox-website.vercel.app/self-storage/central-coast/rutherford/ | Live
4. Rescue: next 16 | 31 |  | Suburb page | /self-storage/sydney/artarmon/ | storage artarmon |  | 4467 | 10.3 | Rebuild | /locations/artarmon/ | Blacktown NSW | Currently position 10.3 with 0 clicks from 4467 impressions | https://portabox-website.vercel.app/self-storage/sydney/artarmon/ | Live
4. Rescue: next 16 | 32 |  | Suburb page | /self-storage/gold-coast/robina/ | storage robina |  | 4409 | 6.9 | Rebuild | /locations/robina/ | Gilberton QLD | Currently position 6.9 with 5 clicks from 4409 impressions | https://portabox-website.vercel.app/self-storage/gold-coast/robina/ | Live
4. Rescue: next 16 | 33 |  | Suburb page | /self-storage/CHECK/richmond/ | storage richmond |  | 4392 | 24.4 | Rebuild | /locations/richmond/ | confirm | REGION UNCONFIRMED: this suburb name exists in more than one state, confirm before building. Currently position 24.4 with 1 clicks from 4392 impressions | https://portabox-website.vercel.app/self-storage/CHECK/richmond/ | Not built yet | BLOCKED, needs one decision: this suburb name exists in more than one state, so the page would land under the wrong region hub. Confirm the state and it is a few minutes to build.
4. Rescue: next 16 | 34 |  | Suburb page | /self-storage/CHECK/queanbeyan/ | storage queanbeyan |  | 4054 | 6.2 | Rebuild | /locations/queanbeyan/ | confirm | REGION UNCONFIRMED: this suburb name exists in more than one state, confirm before building. Currently position 6.2 with 6 clicks from 4054 impressions | https://portabox-website.vercel.app/self-storage/CHECK/queanbeyan/ | Not built yet | BLOCKED, needs one decision: this suburb name exists in more than one state, so the page would land under the wrong region hub. Confirm the state and it is a few minutes to build.
4. Rescue: next 16 | 35 |  | Suburb page | /self-storage/sydney/alexandria/ | storage alexandria |  | 3912 | 15.1 | Rebuild | /locations/alexandria/ | Blacktown NSW | Currently position 15.1 with 2 clicks from 3912 impressions | https://portabox-website.vercel.app/self-storage/sydney/alexandria/ | Live
4. Rescue: next 16 | 36 |  | Suburb page | /self-storage/sydney/dee-why/ | storage dee why |  | 3909 | 10 | Rebuild | /locations/dee-why/ | Blacktown NSW | Currently position 10.0 with 2 clicks from 3909 impressions | https://portabox-website.vercel.app/self-storage/sydney/dee-why/ | Live
4. Rescue: next 16 | 37 |  | Suburb page | /self-storage/melbourne/cheltenham/ | storage cheltenham |  | 3245 | 22.8 | Rebuild | /locations/cheltenham/ | Laverton North VIC | Currently position 22.8 with 0 clicks from 3245 impressions | https://portabox-website.vercel.app/self-storage/melbourne/cheltenham/ | Live
4. Rescue: next 16 | 38 |  | Suburb page | /self-storage/melbourne/carrum-downs/ | storage carrum downs |  | 3204 | 14.9 | Rebuild | /locations/carrum-downs/ | Laverton North VIC | Currently position 14.9 with 0 clicks from 3204 impressions | https://portabox-website.vercel.app/self-storage/melbourne/carrum-downs/ | Live
4. Rescue: next 16 | 39 |  | Suburb page | /self-storage/gold-coast/currumbin/ | storage currumbin |  | 2881 | 8.2 | Rebuild | /locations/currumbin/ | Gilberton QLD | Currently position 8.2 with 3 clicks from 2881 impressions | https://portabox-website.vercel.app/self-storage/gold-coast/currumbin/ | Live
4. Rescue: next 16 | 40 |  | Suburb page | /self-storage/sydney/hornsby/ | storage hornsby |  | 2849 | 14.1 | Rebuild | /locations/hornsby/ | Blacktown NSW | Currently position 14.1 with 3 clicks from 2849 impressions | https://portabox-website.vercel.app/self-storage/sydney/hornsby/ | Live
4. Rescue: next 16 | 41 |  | Suburb page | /self-storage/CHECK/springwood/ | storage springwood |  | 2275 | 12.8 | Rebuild | /locations/springwood/ | confirm | REGION UNCONFIRMED: this suburb name exists in more than one state, confirm before building. Currently position 12.8 with 0 clicks from 2275 impressions | https://portabox-website.vercel.app/self-storage/CHECK/springwood/ | Not built yet | BLOCKED, needs one decision: this suburb name exists in more than one state, so the page would land under the wrong region hub. Confirm the state and it is a few minutes to build.
4. Rescue: next 16 | 42 |  | Suburb page | /self-storage/sydney/chatswood/ | storage chatswood |  | 2020 | 12.7 | Rebuild | /locations/chatswood/ | Blacktown NSW | Currently position 12.7 with 0 clicks from 2020 impressions | https://portabox-website.vercel.app/self-storage/sydney/chatswood/ | Live
4. Rescue: next 16 | 43 |  | Suburb page | /self-storage/brisbane/logan/ | storage logan |  | 1768 | 12.7 | Rebuild | /locations/logan/ | Gilberton QLD | Currently position 12.7 with 4 clicks from 1768 impressions | https://portabox-website.vercel.app/self-storage/brisbane/logan/ | Live
4. Rescue: next 16 | 44 |  | Suburb page | /self-storage/CHECK/mitchell/ | storage mitchell |  | 1766 | 14.2 | Rebuild | /locations/mitchell/ | confirm | REGION UNCONFIRMED: this suburb name exists in more than one state, confirm before building. Currently position 14.2 with 2 clicks from 1766 impressions | https://portabox-website.vercel.app/self-storage/CHECK/mitchell/ | Not built yet | BLOCKED, needs one decision: this suburb name exists in more than one state, so the page would land under the wrong region hub. Confirm the state and it is a few minutes to build.
4. Rescue: next 16 | 45 |  | Suburb page | /self-storage/gold-coast/nerang/ | storage nerang |  | 1715 | 13.9 | Rebuild | /locations/nerang/ | Gilberton QLD | Currently position 13.9 with 5 clicks from 1715 impressions | https://portabox-website.vercel.app/self-storage/gold-coast/nerang/ | Live
5. Rescue: remainder | 46 |  | Suburb page | /self-storage/gold-coast/hope-island/ | storage hope island |  | 1692 | 17.6 | Rebuild | /locations/hope-island/ | Gilberton QLD | Currently position 17.6 with 4 clicks from 1692 impressions | https://portabox-website.vercel.app/self-storage/gold-coast/hope-island/ | Live
5. Rescue: remainder | 47 |  | Suburb page | /self-storage/sydney/bondi-junction/ | storage bondi junction |  | 1635 | 17 | Rebuild | /locations/bondi-junction/ | Blacktown NSW | Currently position 17.0 with 2 clicks from 1635 impressions | https://portabox-website.vercel.app/self-storage/sydney/bondi-junction/ | Live
5. Rescue: remainder | 48 |  | Suburb page | /self-storage/brisbane/milton/ | storage milton |  | 1623 | 24 | Rebuild | /locations/milton/ | Gilberton QLD | Currently position 24.0 with 1 clicks from 1623 impressions | https://portabox-website.vercel.app/self-storage/brisbane/milton/ | Live
5. Rescue: remainder | 49 |  | Suburb page | /self-storage/brisbane/indooroopilly/ | storage indooroopilly |  | 1534 | 19.6 | Rebuild | /locations/indooroopilly/ | Gilberton QLD | Currently position 19.6 with 1 clicks from 1534 impressions | https://portabox-website.vercel.app/self-storage/brisbane/indooroopilly/ | Live
5. Rescue: remainder | 50 |  | Suburb page | /self-storage/sydney/northern-beaches/ | storage northern beaches |  | 1461 | 13.1 | Rebuild | /locations/northern-beaches/ | Blacktown NSW | Currently position 13.1 with 3 clicks from 1461 impressions | https://portabox-website.vercel.app/self-storage/sydney/northern-beaches/ | Live
5. Rescue: remainder | 51 |  | Suburb page | /self-storage/sydney/burwood/ | storage burwood |  | 1390 | 18.1 | Rebuild | /locations/burwood/ | Blacktown NSW | Currently position 18.1 with 0 clicks from 1390 impressions | https://portabox-website.vercel.app/self-storage/sydney/burwood/ | Live
5. Rescue: remainder | 52 |  | Suburb page | /self-storage/brisbane/caboolture/ | storage caboolture |  | 1352 | 16.2 | Rebuild | /locations/caboolture/ | Gilberton QLD | Currently position 16.2 with 6 clicks from 1352 impressions | https://portabox-website.vercel.app/self-storage/brisbane/caboolture/ | Live
5. Rescue: remainder | 53 |  | Suburb page | /self-storage/central-coast/maitland/ | storage maitland |  | 1260 | 11.3 | Rebuild | /locations/maitland/ | Blacktown NSW | Currently position 11.3 with 4 clicks from 1260 impressions | https://portabox-website.vercel.app/self-storage/central-coast/maitland/ | Live
5. Rescue: remainder | 54 |  | Suburb page | /self-storage/sydney/waterloo/ | storage waterloo |  | 1155 | 11.9 | Rebuild | /locations/waterloo/ | Blacktown NSW | Currently position 11.9 with 0 clicks from 1155 impressions | https://portabox-website.vercel.app/self-storage/sydney/waterloo/ | Live
5. Rescue: remainder | 55 |  | Suburb page | /self-storage/sydney/st-marys/ | storage st marys |  | 1062 | 13.7 | Rebuild | /locations/st-marys/ | Blacktown NSW | Currently position 13.7 with 1 clicks from 1062 impressions | https://portabox-website.vercel.app/self-storage/sydney/st-marys/ | Live
5. Rescue: remainder | 56 |  | Suburb page | /self-storage/melbourne/clayton/ | storage clayton |  | 1004 | 10.1 | Rebuild | /locations/clayton/ | Laverton North VIC | Currently position 10.1 with 0 clicks from 1004 impressions | https://portabox-website.vercel.app/self-storage/melbourne/clayton/ | Live
5. Rescue: remainder | 57 |  | Suburb page | /self-storage/sydney/manly/ | storage manly |  | 909 | 14.8 | Rebuild | /locations/manly/ | Blacktown NSW | Currently position 14.8 with 1 clicks from 909 impressions | https://portabox-website.vercel.app/self-storage/sydney/manly/ | Live
5. Rescue: remainder | 58 |  | Suburb page | /self-storage/central-coast/morisset/ | storage morisset |  | 849 | 9.2 | Rebuild | /locations/morisset/ | Blacktown NSW | Currently position 9.2 with 1 clicks from 849 impressions | https://portabox-website.vercel.app/self-storage/central-coast/morisset/ | Live
5. Rescue: remainder | 59 |  | Suburb page | /self-storage/sydney/camperdown/ | storage camperdown |  | 793 | 15.1 | Rebuild | /locations/camperdown/ | Blacktown NSW | Currently position 15.1 with 4 clicks from 793 impressions | https://portabox-website.vercel.app/self-storage/sydney/camperdown/ | Live
5. Rescue: remainder | 60 |  | Suburb page | /self-storage/sydney/rosebery/ | storage rosebery |  | 426 | 23.1 | Rebuild | /locations/rosebery/ | Blacktown NSW | Currently position 23.1 with 0 clicks from 426 impressions | https://portabox-website.vercel.app/self-storage/sydney/rosebery/ | Live
5. Rescue: remainder | 61 |  | Suburb page | /self-storage/brisbane/coorparoo/ | storage coorparoo |  | 35 | 8.4 | Rebuild | /locations/coorparoo/ | Gilberton QLD | Currently position 8.4 with 0 clicks from 35 impressions | https://portabox-website.vercel.app/self-storage/brisbane/coorparoo/ | Live
5. Rescue: remainder | 62 |  | Suburb page | /self-storage/melbourne/collingwood/ | storage collingwood |  | 25 | 8.6 | Rebuild | /locations/collingwood/ | Laverton North VIC | Currently position 8.6 with 1 clicks from 25 impressions | https://portabox-website.vercel.app/self-storage/melbourne/collingwood/ | Live
6. Format pages | 63 |  | Format page | /storage-pods/ | storage pods | 480 |  |  | Build |  |  | Consolidates storage pods, pods storage, storage pod and pod storage. Those four currently rank 26 to 42 with no page owning them | https://portabox-website.vercel.app/storage-pods/ | Live
6. Format pages | 64 |  | Format page | /mobile-storage/ | mobile storage | 720 |  |  | Build |  |  | Difficulty 16, CPC $16.76. Highest commercial value for the lowest difficulty in the set | https://portabox-website.vercel.app/mobile-storage/ | Live
6. Format pages | 65 |  | Format page | /portable-storage-containers/ | portable storage containers | 390 |  |  | Build |  |  | Difficulty 17. Use this instead of "storage containers", which is a food container query | https://portabox-website.vercel.app/portable-storage-containers/ | Live
6. Format pages | 66 |  | Format page | /moving-pods/ | moving pods | 320 |  |  | Build |  |  | Already converts at 12.9% from position 3.5 with no dedicated page | https://portabox-website.vercel.app/moving-pods/ | Live
6. Format pages | 67 |  | Format page | /storage-size-calculator/ | storage size calculator |  |  |  | Build |  |  | Promote the existing calculator widget to its own page. Calculators earn backlinks | https://portabox-website.vercel.app/storage-size-calculator/ | Live
6. Format pages | 68 |  | Format page | /container-sizes/ | pods sizes |  |  |  | Rebuild |  |  | Exists. Ranks position 1.7 and converts 0.13%. Rewrite the title and meta only | https://portabox-website.vercel.app/container-sizes/ | Live
7. Interstate routes | 69 |  | Route page | /moving/sydney-to-melbourne/ | removalists sydney to melbourne | 480 |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/sydney-to-melbourne/ | Live
7. Interstate routes | 70 |  | Route page | /moving/sydney-to-brisbane/ | removalists sydney to brisbane |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/sydney-to-brisbane/ | Live
7. Interstate routes | 71 |  | Route page | /moving/sydney-to-adelaide/ | removalists sydney to adelaide |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/sydney-to-adelaide/ | Live
7. Interstate routes | 72 |  | Route page | /moving/sydney-to-gold-coast/ | removalists sydney to gold coast |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/sydney-to-gold-coast/ | Live
7. Interstate routes | 73 |  | Route page | /moving/melbourne-to-sydney/ | removalists melbourne to sydney |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/melbourne-to-sydney/ | Live
7. Interstate routes | 74 |  | Route page | /moving/melbourne-to-brisbane/ | removalists melbourne to brisbane |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/melbourne-to-brisbane/ | Live
7. Interstate routes | 75 |  | Route page | /moving/melbourne-to-adelaide/ | removalists melbourne to adelaide |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/melbourne-to-adelaide/ | Live
7. Interstate routes | 76 |  | Route page | /moving/melbourne-to-gold-coast/ | removalists melbourne to gold coast |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/melbourne-to-gold-coast/ | Live
7. Interstate routes | 77 |  | Route page | /moving/brisbane-to-sydney/ | removalists brisbane to sydney |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/brisbane-to-sydney/ | Live
7. Interstate routes | 78 |  | Route page | /moving/brisbane-to-melbourne/ | removalists brisbane to melbourne |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/brisbane-to-melbourne/ | Live
7. Interstate routes | 79 |  | Route page | /moving/brisbane-to-adelaide/ | removalists brisbane to adelaide |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/brisbane-to-adelaide/ | Live
7. Interstate routes | 80 |  | Route page | /moving/brisbane-to-gold-coast/ | removalists brisbane to gold coast |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/brisbane-to-gold-coast/ | Live
7. Interstate routes | 81 |  | Route page | /moving/adelaide-to-sydney/ | removalists adelaide to sydney |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/adelaide-to-sydney/ | Live
7. Interstate routes | 82 |  | Route page | /moving/adelaide-to-melbourne/ | removalists adelaide to melbourne |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/adelaide-to-melbourne/ | Live
7. Interstate routes | 83 |  | Route page | /moving/adelaide-to-brisbane/ | removalists adelaide to brisbane |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/adelaide-to-brisbane/ | Live
7. Interstate routes | 84 |  | Route page | /moving/adelaide-to-gold-coast/ | removalists adelaide to gold coast |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/adelaide-to-gold-coast/ | Live
7. Interstate routes | 85 |  | Route page | /moving/gold-coast-to-sydney/ | removalists gold coast to sydney |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/gold-coast-to-sydney/ | Live
7. Interstate routes | 86 |  | Route page | /moving/gold-coast-to-melbourne/ | removalists gold coast to melbourne |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/gold-coast-to-melbourne/ | Live
7. Interstate routes | 87 |  | Route page | /moving/gold-coast-to-brisbane/ | removalists gold coast to brisbane |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/gold-coast-to-brisbane/ | Live
7. Interstate routes | 88 |  | Route page | /moving/gold-coast-to-adelaide/ | removalists gold coast to adelaide |  |  |  | Build |  |  | Interstate removalists is 4,400/mo at $45.14 CPC. Sydney to Melbourne measured at 480/mo, difficulty 22, CPC $46.63 | https://portabox-website.vercel.app/moving/gold-coast-to-adelaide/ | Live
8. Box shop | 89 |  | Boxes | /moving-boxes/ | moving boxes | 18100 |  |  | Build | 18 x /boxes/* pages 301 here |  | Replaces 18 thin box pages earning 42,803 impressions and 63 clicks | https://portabox-website.vercel.app/moving-boxes/ | Live
8. Box shop | 90 |  | Boxes | /moving-boxes/brisbane/ | moving boxes brisbane |  |  |  | Build | 18 x /boxes/* pages 301 here |  | City variant | https://portabox-website.vercel.app/moving-boxes/brisbane/ | Live
8. Box shop | 91 |  | Boxes | /packing-supplies/ | packing supplies |  |  |  | Build | 18 x /boxes/* pages 301 here |  | Bubble wrap, tape, wardrobe boxes | https://portabox-website.vercel.app/packing-supplies/ | Live
8. Box shop | 92 |  | Boxes | /box-shop/ | box shop |  |  |  | Build | 18 x /boxes/* pages 301 here |  | Hub. 301 the 18 old box URLs into these four | https://portabox-website.vercel.app/box-shop/ | Live
9. Comparison and trust | 93 |  | Comparison | /compare/mobile-storage-vs-self-storage/ | mobile storage vs self storage |  |  |  | Build |  |  | Category comparison. Usually the biggest comparison driver | https://portabox-website.vercel.app/compare/mobile-storage-vs-self-storage/ | Live
9. Comparison and trust | 94 |  | Comparison | /compare/storage-pods-vs-storage-unit/ | storage unit vs pods |  |  |  | Build |  |  |  | https://portabox-website.vercel.app/compare/storage-pods-vs-storage-unit/ | Live
9. Comparison and trust | 95 |  | Comparison | /compare/moving-pods-vs-truck-hire/ | moving pods vs truck |  |  |  | Build |  |  |  | https://portabox-website.vercel.app/compare/moving-pods-vs-truck-hire/ | Live
9. Comparison and trust | 96 |  | Comparison | /compare/portabox-vs-taxibox/ | portabox vs taxibox |  |  |  | Build |  |  | Head to head only. Do not build pages for "storage king ipswich" style queries, they are navigational | https://portabox-website.vercel.app/compare/portabox-vs-taxibox/ | Live
9. Comparison and trust | 97 |  | Trust | /reviews/ | portabox reviews |  |  |  | Build |  |  | People search brand plus reviews and currently land on Google, not on you | https://portabox-website.vercel.app/reviews/ | Live
9. Comparison and trust | 98 |  | Trust | /formerly-pods-australia/ | auspods |  | 934 |  | Build |  |  | LAUNCH CRITICAL. auspods converts at 49.2% and aus pods at 62%. Those searchers must land somewhere once the domain redirects | https://portabox-website.vercel.app/formerly-pods-australia/ | Live
10. Consolidation review | 99 |  | Review | /locations/melbourne/ |  |  | 16135 | 27.4 | Consolidate or drop | /locations/melbourne/ |  | Ranks position 27.4. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/melbourne/ | Live (301) | DONE — merged into its region hub. The hub already covers this ground, so the old URL 301s to /self-storage/melbourne/ rather than running a second page against it.
10. Consolidation review | 100 |  | Review | /locations/mornington/ |  |  | 3948 | 54.9 | Consolidate or drop | /locations/mornington/ |  | Ranks position 54.9. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/mornington/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/mornington/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Mornington, Melbourne, Victoria, 3931, Australia — 61 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 101 |  | Review | /locations/penrith/ |  |  | 2528 | 34.4 | Consolidate or drop | /locations/penrith/ |  | Ranks position 34.4. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/penrith/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/penrith/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Penrith, Sydney, New South Wales, 2750, Australia — 25 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 102 |  | Review | /locations/burleigh/ |  |  | 2432 | 41.8 | Consolidate or drop | /locations/burleigh/ |  | Ranks position 41.8. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/burleigh/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/gold-coast/burleigh/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Burleigh Heads, Gold Coast, Queensland, Australia — 56 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 103 |  | Review | /locations/port-melbourne/ |  |  | 2387 | 39.4 | Consolidate or drop | /locations/port-melbourne/ |  | Ranks position 39.4. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/port-melbourne/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/port-melbourne/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Port Melbourne, Melbourne, Victoria, 3207, Australia — 13 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 104 |  | Review | /locations/belmont/ |  |  | 2072 | 27.1 | Consolidate or drop | /locations/belmont/ |  | Ranks position 27.1. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/belmont/ | Not built yet | BLOCKED, needs one decision: this name is a real suburb in more than one of our cities, so geocoding cannot pick the hub for us. Candidates, each in depot range: Brisbane (37 km, Queensland); Sydney (137 km, New South Wales); Melbourne (71 km, Victoria). Say which one and the page is a few minutes to build.
10. Consolidation review | 105 |  | Review | /locations/south-melbourne/ |  |  | 1909 | 45 | Consolidate or drop | /locations/south-melbourne/ |  | Ranks position 45.0. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/south-melbourne/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/south-melbourne/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: South Melbourne, Melbourne, Victoria, 3205, Australia — 18 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 106 |  | Review | /locations/tullamarine/ |  |  | 1564 | 32.4 | Consolidate or drop | /locations/tullamarine/ |  | Ranks position 32.4. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/tullamarine/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/tullamarine/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Tullamarine, Melbourne, Victoria, 3043, Australia — 19 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 107 |  | Review | /locations/moorabbin/ |  |  | 1492 | 40.7 | Consolidate or drop | /locations/moorabbin/ |  | Ranks position 40.7. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/moorabbin/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/moorabbin/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Moorabbin, Melbourne, Victoria, 3189, Australia — 33 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 108 |  | Review | /locations/yatala/ |  |  | 1286 | 45.2 | Consolidate or drop | /locations/yatala/ |  | Ranks position 45.2. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/yatala/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/brisbane/yatala/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Yatala, Logan City, Queensland, 4207, Australia — 8 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 109 |  | Review | /locations/capalaba/ |  |  | 1165 | 34 | Consolidate or drop | /locations/capalaba/ |  | Ranks position 34.0. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/capalaba/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/brisbane/capalaba/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Capalaba, Logan City, Brisbane, Redland City, Queensland, Australia — 32 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 110 |  | Review | /locations/north-sydney/ |  |  | 1115 | 48.2 | Consolidate or drop | /locations/north-sydney/ |  | Ranks position 48.2. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/north-sydney/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/north-sydney/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: North Sydney, New South Wales, 2060, Australia — 37 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 111 |  | Review | /locations/fremantle/ |  |  | 1060 | 30 | Consolidate or drop | /locations/fremantle/ |  | Ranks position 30.0. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/fremantle/ | Live (301) | DONE — dropped as a service page. Fremantle is in WA and the nearest depot is Adelaide, well past the 200 km standard-delivery range, so a page promising service there would not be true. The old URL 301s to /locations/regional-australia/, which is where a WA enquiry should land.
10. Consolidation review | 112 |  | Review | /locations/brookvale/ |  |  | 1008 | 58.8 | Consolidate or drop | /locations/brookvale/ |  | Ranks position 58.8. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/brookvale/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/brookvale/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Brookvale, Northern Beaches, Sydney, New South Wales, Australia — 43 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 113 |  | Review | /locations/marrickville/ |  |  | 966 | 37 | Consolidate or drop | /locations/marrickville/ |  | Ranks position 37.0. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/marrickville/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/marrickville/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Marrickville, Inner West, Sydney, New South Wales, 2204, Australia — 36 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 114 |  | Review | /locations/eastern-suburbs/ |  |  | 940 | 35.6 | Consolidate or drop | /locations/eastern-suburbs/ |  | Ranks position 35.6. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/eastern-suburbs/ | Live (301) | DONE — merged, not rebuilt. "Eastern Suburbs" is a region, not a suburb, so there is nothing to geocode and no single page it maps to. The old URL 301s to /self-storage/sydney/, which lists every Sydney suburb page beneath it, Bondi Junction among them.
10. Consolidation review | 115 |  | Review | /locations/kensington/ |  |  | 886 | 48.9 | Consolidate or drop | /locations/kensington/ |  | Ranks position 48.9. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/kensington/ | Not built yet | BLOCKED, needs one decision: this name is a real suburb in more than one of our cities, so geocoding cannot pick the hub for us. Candidates, each in depot range: Sydney (42 km, New South Wales); Melbourne (15 km, Victoria); Adelaide (30 km, South Australia). Say which one and the page is a few minutes to build.
10. Consolidation review | 116 |  | Review | /locations/unanderra/ |  |  | 736 | 35.4 | Consolidate or drop | /locations/unanderra/ |  | Ranks position 35.4. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/unanderra/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/wollongong/unanderra/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Unanderra, Wollongong, New South Wales, Australia — 97 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 117 |  | Review | /locations/north-melbourne/ |  |  | 730 | 64 | Consolidate or drop | /locations/north-melbourne/ |  | Ranks position 64.0. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/north-melbourne/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/north-melbourne/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: North Melbourne, Melbourne, Victoria, 3051, Australia — 16 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 118 |  | Review | /locations/chermside/ |  |  | 542 | 42.1 | Consolidate or drop | /locations/chermside/ |  | Ranks position 42.1. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/chermside/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/brisbane/chermside/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Chermside, Brisbane, Queensland, 4032, Australia — 58 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 119 |  | Review | /locations/gladesville/ |  |  | 528 | 39.3 | Consolidate or drop | /locations/gladesville/ |  | Ranks position 39.3. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/gladesville/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/gladesville/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Gladesville, Sydney, New South Wales, 2111, Australia — 27 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 120 |  | Review | /locations/altona/ |  |  | 522 | 50.6 | Consolidate or drop | /locations/altona/ |  | Ranks position 50.6. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/altona/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/melbourne/altona/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Altona, Melbourne, Victoria, 3018, Australia — 5 km by road from the Melbourne depot at Laverton North.
10. Consolidation review | 121 |  | Review | /locations/ormeau/ |  |  | 503 | 42.3 | Consolidate or drop | /locations/ormeau/ |  | Ranks position 42.3. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/ormeau/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/gold-coast/ormeau/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Ormeau, Queensland, Australia — 8 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 122 |  | Review | /locations/aspley/ |  |  | 370 | 36.7 | Consolidate or drop | /locations/aspley/ |  | Ranks position 36.7. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/aspley/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/brisbane/aspley/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Aspley, Brisbane, Queensland, Australia — 62 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 123 |  | Review | /locations/brendale/ |  |  | 308 | 43.5 | Consolidate or drop | /locations/brendale/ |  | Ranks position 43.5. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/brendale/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/brisbane/brendale/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Brendale, Brisbane, Queensland, Australia — 70 km by road from the Brisbane depot at Gilberton.
10. Consolidation review | 124 |  | Review | /locations/hawthorn/ |  |  | 184 | 59.5 | Consolidate or drop | /locations/hawthorn/ |  | Ranks position 59.5. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/hawthorn/ | Not built yet | BLOCKED, needs one decision: this name is a real suburb in more than one of our cities, so geocoding cannot pick the hub for us. Candidates, each in depot range: Melbourne (25 km, Victoria); Adelaide (38 km, South Australia). Say which one and the page is a few minutes to build.
10. Consolidation review | 125 |  | Review | /locations/rozelle/ |  |  | 20 | 85.8 | Consolidate or drop | /locations/rozelle/ |  | Ranks position 85.8. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/rozelle/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/rozelle/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Rozelle, Inner West, Sydney, New South Wales, 2039, Australia — 34 km by road from the Sydney depot at Blacktown.
10. Consolidation review | 126 |  | Review | /locations/balmain/ |  |  | 17 | 82.5 | Consolidate or drop | /locations/balmain/ |  | Ranks position 82.5. Decide: merge into its region hub, or rebuild. Do not migrate as is | https://portabox-website.vercel.app/locations/balmain/ | Live (301) | DONE — rebuilt, not migrated as-is. The old URL 301s to /self-storage/sydney/balmain/, a suburb page written from scratch. Which hub it belongs under was settled by geocoding the name: Balmain, Inner West, Sydney, New South Wales, 2041, Australia — 34 km by road from the Sydney depot at Blacktown.